EXPENSE INTELLIGENCE
PLATFORM

Full Project Proposal

A mobile-first, auditable platform for transforming receipts into product-level financial intelligence

| Proposal field | Details |
| --- | --- |
| Prepared for | Terril Joel Nazareth |
| Project type | Individual portfolio and applied software engineering project |
| Planned duration | 12 weeks; approximately 8–10 hours per week |
| Target users | Two household users, designed for later extension |
| Operating-cost ceiling | €5 per month; target normal cost €0–€2 |
| Proposed start | 27 July 2026 |
| Version | 1.0 — 21 July 2026 |

Project thesis Build a reliable data product first. Apply OCR, retrieval and controlled AI only where they reduce manual work without weakening correctness, traceability, privacy or cost control.

# Executive Summary

This proposal defines the development of a mobile-first expense intelligence platform that converts photographed retail receipts and manually entered expenses into auditable item-level financial data. The system will support personal and shared spending, product-level search and price history, category analytics, and later a SQL-grounded financial assistant.

The project addresses a practical gap in common expense trackers: bank transactions show the merchant and total amount but not the products purchased. Receipt images contain this detail, yet extracting it reliably requires more than a single unrestricted LLM call. The proposed solution therefore combines deterministic validation, human review, provider-independent extraction, learned mappings, retrieval, and a restricted AI fallback.

Development will follow a DevOps-first path from the first week. Every milestone must pass automated tests, security and cost checks, deploy to staging, and remain reversible. The project deliberately excludes costly or unnecessary infrastructure such as Kubernetes, virtual machines, managed Azure PostgreSQL, a separate vector database, and multi-agent orchestration.

| Outcome | Target |
| --- | --- |
| Functional | Upload or enter a receipt, verify extracted fields, save validated items, and drill from month to source receipt. |
| Reliability | Prevent duplicate ingestion, reconcile totals, preserve raw and corrected values, and degrade safely when AI providers fail. |
| Engineering | Containerized local environment, infrastructure as code, CI/CD, staged releases, observability and rollback. |
| AI quality | At least 90% precision for automatically approved product mappings; uncertain cases require review. |
| Cost | Operate normally at €0–€2/month and never exceed the €5/month ceiling. |
| Portfolio | Demonstrate data engineering, cloud, AI integration, DevOps, testing and responsible system design. |

# 1. Background and Problem Statement

Personal finance applications commonly import bank transactions and categorize spending at the merchant level. A €34.72 transaction at REWE can be classified as groceries, but it does not reveal how much was spent on milk, vegetables, household products or deposits. That limits product-level budgeting, price comparison and household settlement.

Receipts contain the missing detail but introduce several engineering problems: merchant abbreviations vary, OCR can confuse quantities and prices, discounts and Pfand complicate reconciliation, the same receipt may be uploaded twice, and free AI services may be rate-limited or unavailable. A model that writes directly into financial tables can silently corrupt later analytics.

Core problem How can unstructured receipts be converted into trustworthy product-level financial records while keeping the workflow mobile, explainable, resilient and affordable for a two-user household?

# 2. Project Aim, Objectives and Research Questions

## 2.1 Aim

To design, implement and evaluate a cost-controlled, cloud-deployed expense intelligence platform that converts receipts into validated item-level records and supports auditable household financial analysis.

## 2.2 Objectives

Create a mobile-first workflow for manual receipt entry, camera upload, correction and approval.

Model transactions, receipts, line items, products, categories, mappings, allocations and audit events in PostgreSQL.

Extract receipt fields through replaceable OCR/LLM providers that return strict structured output.

Validate schemas, detect duplicates and reconcile receipt totals before committing financial records.

Learn from approved corrections using exact, merchant-specific and fuzzy mappings; introduce vector retrieval only when justified by data.

Restrict AI enrichment to unresolved sanitized product strings and require evidence and confidence.

Provide drill-through analytics and later answer financial questions through validated read-only SQL.

Apply CI/CD, infrastructure as code, security scanning, observability, staged deployment and rollback from project inception.

Measure correctness, data quality, reliability, privacy, user value and operating cost.

## 2.3 Guiding questions

Can a layered deterministic-first workflow achieve reliable receipt ingestion without depending on a single AI provider?

How much manual review remains necessary after approved corrections are reused?

Can the deployed system stay below €5/month while retaining credible cloud and DevOps practices?

Does the design preserve traceability from every aggregate value to its source receipt and correction history?

# 3. Scope and Product Definition

| Priority | Included capabilities |
| --- | --- |
| Must have | Manual and image-based receipt intake; item-level records; validation and review; duplicate detection; total reconciliation; personal/shared allocation; drill-through dashboard; authentication; audit history; automated deployment and tests. |
| Should have | Bank CSV import; transaction-to-receipt matching; learned merchant mappings; barcode lookup; Open Food Facts enrichment; offline capture queue; retrieval-based normalization. |
| Could have | Controlled product-resolution agent; natural-language financial assistant; merchant price comparison; notifications; budget forecasting. |
| Explicitly excluded | Direct bank API integration, investment advice, native mobile apps, autonomous multi-agent workflows, unrestricted web research, Kubernetes, VMs, Redis, separate vector database and LLM-calculated totals. |

## 3.1 Primary user journey

The user photographs or manually creates a receipt on a phone.

The backend stores the image privately and creates a processing record.

An extraction provider returns schema-constrained receipt and line-item candidates.

Deterministic rules validate types, totals, duplicate risk and confidence.

The user reviews uncertain or inconsistent fields.

The application service saves approved records and an audit trail.

Product mappings are reused on later receipts; unresolved items may be enriched through controlled retrieval or AI.

Dashboards expose Month → Category → Merchant → Receipt → Product drill-through.

# 4. Proposed Solution and Architecture

The solution uses a modular monolith for the API and worker logic. This is easier to deploy and operate than microservices at the current scale, while provider interfaces and service boundaries preserve future extensibility.

| Layer | Responsibility | Proposed technology |
| --- | --- | --- |
| Client | Installable mobile interface, offline capture queue and review | React/Next.js PWA |
| API | Authentication, validation, business rules and queries | Python, FastAPI, Pydantic |
| Data | Relational records, constraints, analytics and mappings | PostgreSQL; pgvector only when justified |
| Object storage | Private receipt images and controlled retention | Azure Blob Storage |
| Processing | Asynchronous extraction, retry and failure states | Background worker or Container Apps job |
| OCR | Receipt fields and raw text | Azure Document Intelligence F0; local fallback |
| Enrichment | Barcode and product metadata | Open Food Facts; cached |
| AI fallback | Structured resolution for unknown products | GitHub Models; optional sanitized fallback |
| Delivery | Build, scan, stage and promote immutable images | GitHub Actions and GHCR |
| Cloud | Scale-to-zero application deployment | Azure Container Apps |
| Observability | Structured logs, health checks and minimal traces | OpenTelemetry-compatible instrumentation |

## 4.1 Processing flow

| Step | Control | Failure behavior |
| --- | --- | --- |
| Capture | Compress image; generate content hash | Queue offline or permit manual entry |
| Extract | Strict schema; provider timeout; limited retries | Switch provider or mark extraction failed |
| Validate | Required fields, numeric types, date and currency rules | Return field-level errors to review |
| Reconcile | Items + deposits − discounts + adjustments = total | Prevent completion above tolerance |
| Resolve products | Exact mapping → merchant mapping → fuzzy retrieval → external source | Leave unresolved when confidence is insufficient |
| Approve | Human confirmation for uncertainty | Nothing reaches financial tables silently |
| Persist | Application service transaction and audit event | Atomic rollback on failure |
| Analyze | Read-only queries linked to source records | Reject unsafe or unverifiable queries |

## 4.2 Core data model

| Entity | Purpose | Critical integrity rule |
| --- | --- | --- |
| User / Household | Identity and data isolation | Every financial record belongs to one household |
| Transaction | Bank or manual payment record | Money stored as fixed-precision decimal |
| Receipt | Merchant, date, total, image and status | Unique image hash within household |
| ReceiptItem | Raw description, quantity, unit price and total | Approved items reconcile to receipt |
| Product / Category | Normalized product identity and hierarchy | Raw text is never overwritten |
| ProductMapping | Merchant alias and approved normalization | Only approved mappings can auto-resolve |
| ExpenseAllocation | Payer, beneficiary and split | Allocations sum exactly to expense amount |
| ResolutionAttempt | Provider, evidence, confidence and decision | Every automated proposal is traceable |
| AuditEvent | State changes and corrections | Append-only user/action/timestamp history |

# 5. Resource Selection and Critical Evaluation

| Resource | Why used | Risk / limitation | Decision |
| --- | --- | --- | --- |
| Next.js PWA | One mobile-friendly codebase with install and offline capabilities | PWA complexity can consume time | Use a narrow responsive UI; no native apps |
| FastAPI | Fits Python/data skills; typed async APIs | Routes can accumulate business logic | Use service and repository boundaries |
| PostgreSQL | Transactions, constraints and analytical SQL | Schema evolution requires discipline | Essential; migrations from day one |
| Neon Free | Hosted PostgreSQL with inactivity suspension | Free limits and cold starts | Use for portfolio scale; abstract connection config |
| pgvector | Similarity retrieval in existing database | Premature without enough corrections | Defer until evaluation data justifies it |
| Azure Container Apps | Azure experience and scale-to-zero containers | Logs and replica settings can create costs | Min 0, max 1; staging and production controls |
| Blob Storage | Cheap private object storage | Privacy and indefinite retention | Private containers, signed access, lifecycle policy |
| Document Intelligence | Purpose-built receipt extraction | German retail lines remain imperfect | Use free quota; always provide review/fallback |
| Local OCR | Provider independence and no API bill | Higher CPU use and weaker structure | Fallback/development path, not mandatory cloud default |
| Open Food Facts | Free structured product data | Incomplete records and rate limits | Cache; never treat absence as proof |
| GitHub Models | Free structured LLM experimentation | Rate limits and no production SLA | Optional fallback behind provider interface |
| LangGraph | Explicit stateful agent workflow | Overengineering for a short fixed flow | Adopt only if plain Python becomes unclear |
| GitHub Actions/GHCR | CI/CD and immutable container delivery | Workflow minutes and image growth | Targeted pipelines and retention rules |
| Terraform or Bicep | Reproducible infrastructure | Two IaC languages add needless work | Choose Bicep for Azure-focused first release |
| Pytest/Playwright | Protect money logic and critical journeys | Too many end-to-end tests become flaky | Test pyramid; few high-value browser tests |

# 6. DevOps and Delivery Strategy

DevOps is part of the product definition, not a final packaging activity. The first deployment will contain only health endpoints and an empty PWA, but it will establish the same path later features use.

## 6.1 Environments and release path

| Environment | Purpose | Promotion rule |
| --- | --- | --- |
| Local | Fast feedback using containers and seeded data | Formatting, unit tests and migrations pass |
| CI | Reproducible validation on every pull request | All required checks pass before merge |
| Staging | Integrated cloud validation and smoke tests | Feature acceptance criteria and cost gate pass |
| Production | Stable two-user release | Manual approval promotes the exact staged image |

## 6.2 Pull-request quality gates

Ruff formatting and linting; mypy type checking; Pytest unit/integration tests.

Frontend linting, type checking and production build.

Database migration validation against a clean database.

Secret, dependency, code and container vulnerability scanning.

Immutable backend and frontend container builds tagged with the commit SHA.

No merge when a mandatory check fails.

## 6.3 Deployment and rollback

A merge to main builds and pushes immutable images, applies safe infrastructure changes, runs migrations, deploys staging and executes smoke tests. A version tag triggers production approval. Production uses the already-tested image rather than rebuilding it. Rollback redeploys the previous image; database migrations must be backward compatible or include an explicit recovery procedure.

## 6.4 Observability and DevSecOps

| Control | Implementation |
| --- | --- |
| Health | /health/live and /health/ready; deployment version exposed without secrets |
| Logs | Structured request/correlation IDs, duration, status and provider; never OCR text or financial data |
| Security | Non-root containers, least privilege, private blobs, expiring URLs and isolated households |
| Secrets | Cloud/GitHub environment secrets; no credentials committed |
| AI controls | Feature flags, quotas, tool-call limits, timeouts and kill switch |
| Cost | Azure alerts at €1, €3 and €5; usage reviewed at every milestone |

# 7. Implementation Plan and Milestones

| Milestone | Week | Deliverable | Acceptance gate |
| --- | --- | --- | --- |
| M0 Engineering baseline | 1 | Repository, containers, CI, IaC skeleton, staging health deployment | All quality checks pass; reproducible staging deployment |
| M1 Manual data product | 2–3 | Receipt/item CRUD, schema, migrations and drill-through dashboard | A milk purchase is traceable from month to source item |
| M2 Household release | 4–5 | Shared allocations, auth, mobile PWA and production release | Two users are isolated; split arithmetic reconciles |
| M3 Reliable ingestion | 6–8 | Upload queue, OCR, review, duplicate checks and total reconciliation | 8/10 clear receipts become usable after review |
| M4 Learned normalization | 9–10 | Approved mappings, fuzzy retrieval and external enrichment | Repeated corrections resolve without external calls |
| M5 Controlled AI | 11 | Evidence-based fallback with confidence policy | No unsupported result is automatically accepted |
| M6 Evaluation/release | 12 | SQL-grounded assistant, metrics, documentation and demo | Overall evaluation ≥80%; no critical defect; cost <€5 |

# 8. Twelve-Week Work Breakdown

| Week | Focus | Planned work | Definition of done |
| --- | --- | --- | --- |
| 1 | Engineering foundation | Requirements, ADRs, schema draft, repository, Docker, CI, Bicep skeleton, staging health deployment. | Deployment is reproducible from an empty environment. |
| 2 | Manual receipt API | Database migrations, validation models, receipt/item/category endpoints and unit tests. | A three-item receipt can be created and retrieved correctly. |
| 3 | Dashboard and traceability | Monthly/category/merchant/receipt/product drill-through; price history; source links. | All displayed totals reconcile with source items. |
| 4 | Shared money logic | Payer/beneficiary allocation, budgets, settlement and Decimal-based arithmetic. | Fixed and percentage splits reconcile without rounding error. |
| 5 | Mobile production release | PWA shell, authentication, household isolation, deployment promotion and smoke tests. | Both users can securely use the application on phones. |
| 6 | Capture pipeline | Camera upload, compression, private storage, offline queue, job status and retry states. | Offline capture uploads exactly once after reconnection. |
| 7 | Structured extraction | Provider interface, OCR integration, raw output retention, confidence and correction UI. | Merchant/date/total accuracy reaches 90% on clear test receipts. |
| 8 | Reconciliation | Discount, Pfand and adjustment handling; duplicate hash; receipt-to-transaction suggestion. | Unexplained differences above tolerance cannot complete. |
| 9 | Mapping feedback loop | Exact and merchant-specific aliases, corrections, fuzzy matching and evaluation dataset. | Approved repeated items resolve locally. |
| 10 | Product enrichment | Barcode/Open Food Facts lookup, evidence, caching, rate limiting and optional embeddings. | Automatic mappings reach ≥90% precision and retain provenance. |
| 11 | Controlled AI fallback | Sanitized inputs, structured candidates, evidence, confidence policy, quotas and human approval. | Ambiguous/no-evidence cases remain unresolved. |
| 12 | Assistant and release | Read-only validated SQL, security/cost review, test report, README, demo data and video. | Monetary answers link to contributing records; release gate passes. |

# 9. Gantt Chart

Schedule: 27 July–18 October 2026. ■ indicates active work. The plan intentionally overlaps deployment and feature work because every slice is released through the established pipeline.

| Workstream | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Scope, schema and ADRs | ■ |  |  |  |  |  |  |  |  |  |  |  |
| Repository, CI/CD and IaC | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |
| Manual receipt workflow |  | ■ |  |  |  |  |  |  |  |  |  |  |
| Dashboard and traceability |  |  | ■ |  |  |  |  |  |  |  |  |  |
| Shared expenses and budgets |  |  |  | ■ |  |  |  |  |  |  |  |  |
| PWA, auth and production |  |  |  | ■ | ■ |  |  |  |  |  |  |  |
| Capture and background processing |  |  |  |  |  | ■ |  |  |  |  |  |  |
| OCR and review |  |  |  |  |  |  | ■ |  |  |  |  |  |
| Reconciliation and duplicates |  |  |  |  |  |  |  | ■ |  |  |  |  |
| Mappings and retrieval |  |  |  |  |  |  |  |  | ■ |  |  |  |
| Product enrichment |  |  |  |  |  |  |  |  |  | ■ |  |  |
| Controlled AI fallback |  |  |  |  |  |  |  |  |  |  | ■ |  |
| Assistant, evaluation and release |  |  |  |  |  |  |  |  |  |  |  | ■ |

# 10. Testing and Evaluation Plan

## 10.1 Evaluation dataset

Create a fixed, privacy-controlled benchmark of approximately 30 receipt images and at least 200 line items. It should include multiple German retailers, repeated products, abbreviations, unclear images, discounts, Pfand, weighted goods, multi-quantity items and intentionally duplicated uploads. Ground truth must be manually verified before measuring models.

| Dimension | Weight | Evidence and threshold |
| --- | --- | --- |
| Functional correctness | 25% | Acceptance tests; zero unresolved money-calculation defects |
| Data quality | 20% | Merchant/date/total ≥90%; auto-approved mappings ≥90% precision |
| Reliability | 15% | Retry, timeout, duplicate, idempotency and fallback tests |
| Security and privacy | 15% | Household-isolation tests; secret handling; no sensitive logs |
| Cost efficiency | 15% | Monthly forecast and measured provider/storage usage below €5 |
| User value | 10% | Two-user feedback; time-to-correct; manual-review rate |

## 10.2 Metrics

OCR field accuracy and line-item precision/recall.

Receipt reconciliation pass rate and unexplained-difference rate.

Normalization top-1 accuracy and precision of automatic approval.

Manual-review percentage, correction reuse rate and unresolved-item rate.

Duplicate prevention rate and idempotent retry success.

Processing latency, external calls per receipt and estimated cost per receipt.

Unsupported-answer rate for AI enrichment and financial assistant queries.

Primary AI principle Optimize the precision of automatic approval, not the percentage automated. Asking the user is preferable to contaminating financial records.

## 10.3 Milestone release rule

A milestone is accepted only when its overall weighted score is at least 80%, CI and staging smoke tests pass, no critical security or financial-correctness defect remains, rollback/fallback is documented, and the projected monthly cost remains below €5.

# 11. Cost Plan and Guardrails

| Component | Target monthly cost | Guardrail |
| --- | --- | --- |
| GitHub repository, Actions, GHCR and Models | €0 | Use student/free allowances; paid model use disabled |
| Neon PostgreSQL | €0 | Free plan; monitor storage and inactivity behavior |
| Azure Container Apps | €0–€1 | Consumption; min replicas 0, max 1; cap logs |
| Azure Blob Storage | €0–€0.50 | Compression, private storage and lifecycle deletion |
| Document Intelligence | €0 | Use free quota; disable processing at quota limit |
| External product APIs | €0 | Cache results; rate-limit; no paid search |
| Contingency | Up to €3.50 | Hard project ceiling remains €5 |

Budget alerts at €1, €3 and €5.

No automatic upgrade from a free tier and no subscription purchase for the project.

Maximum one active replica and limited retention for application logs.

Feature flags independently disable OCR, enrichment and LLM processing.

Maximum two AI tool calls for an unresolved product; cache every approved answer.

Avoid Azure PostgreSQL, AI Search, VMs, Kubernetes, NAT Gateway and always-on workers.

Review measured cost and projected full-month cost at every milestone.

# 12. Risk Register

| Risk | L/I | Mitigation | Trigger / response |
| --- | --- | --- | --- |
| OCR misreads prices or quantities | H/H | Strict schema, confidence, total reconciliation and review | Difference exceeds tolerance → block completion |
| AI invents a product mapping | M/H | Evidence requirement and confidence thresholds | No evidence or <0.70 → unresolved |
| Duplicate receipt creates double spending | M/H | Image hash, merchant/date/total checks and idempotency key | Probable match → require user decision |
| Provider unavailable or rate-limited | H/M | Timeouts, limited retry, fallback and manual path | Quota/failure → disable provider and continue manually |
| Household data exposure | L/H | Authorization at service/query layer and isolation tests | Any cross-user access → stop release |
| Cloud cost exceeds plan | M/H | Scale-to-zero, alerts and feature kill switches | Projected cost >€5 → disable costly feature |
| Scope expansion delays core product | H/M | Must/should/could priorities and milestone gates | Missed gate → cut could-have work |
| Free service terms change | M/M | Provider interfaces and portable containers | Re-evaluate or replace provider |
| Insufficient correction data for RAG | H/L | Use deterministic and fuzzy mappings first | Do not add embeddings until benchmark shows value |
| Database migration breaks release | L/H | Backward-compatible migrations and staged testing | Smoke failure → redeploy previous image and restore safely |

# 13. Security, Privacy and Responsible AI

Store receipt images in private containers and issue short-lived signed access URLs.

Transmit only sanitized product descriptions to optional third-party LLM providers; never send bank data, full receipts, addresses or user identities.

Apply authorization to every household-scoped query rather than relying only on client-side filtering.

Encrypt data in transit, use managed platform encryption at rest and rotate credentials when exposed.

Never log images, OCR text, access tokens, bank references or personal financial values.

Maintain raw extraction, corrected value, provider/model version, confidence, evidence and approving user.

Restrict the financial assistant to read-only, parameterized, allow-listed SQL; the LLM must not calculate totals itself.

Define retention and deletion behavior for original images, temporary uploads and audit records.

# 14. Deliverables

| Category | Deliverables |
| --- | --- |
| Product | Installable PWA, FastAPI service, PostgreSQL schema, receipt worker, dashboard and review interface |
| Cloud/DevOps | Containers, Docker Compose, Bicep, CI/CD workflows, staging/production release and rollback guide |
| Quality | Automated test suite, benchmark dataset definition, evaluation report and security/cost checklist |
| Documentation | Architecture decision records, API/schema documentation, setup and deployment guide, operating runbook |
| Portfolio | Public-safe demo data, screenshots, architecture diagram, two-minute demo video and concise CV bullet |

# 15. Success Criteria and Expected Outcome

A user can capture, review and approve a receipt from a phone.

Every dashboard amount can be traced to validated receipt items or transactions.

Duplicate and inconsistent receipts are blocked or explicitly reviewed.

Repeated corrected product descriptions resolve locally without unnecessary external calls.

Unknown products are never silently invented or written directly by an agent.

The same immutable release artifact is tested in staging and promoted to production.

The service remains usable when OCR/LLM providers are unavailable through review or manual entry.

Normal monthly operating cost is €0–€2 and the hard ceiling of €5 is preserved.

Expected portfolio outcome A deployed data and AI engineering project that demonstrates reliable ingestion of unstructured data, relational modelling, cloud-native delivery, observability, cost control, responsible AI integration and human-in-the-loop quality assurance.

# 16. Project Governance and Decision Rules

Terril is the sole implementer and product owner. Architectural choices are recorded as short Architecture Decision Records. At the end of each week, the project is reviewed using a simple verdict: Accept, Revise or Reject. A feature moves forward only after its acceptance gate passes.

| Decision | Meaning | Action |
| --- | --- | --- |
| Accept | Acceptance criteria and release gates pass | Promote and start the next planned slice |
| Revise | Direction is sound but defects or evidence gaps remain | Fix within the current milestone; do not add scope |
| Reject | The approach violates correctness, privacy, cost or project goals | Remove or redesign before proceeding |

Change-control rule: any new service or major feature must state the problem it solves, measurable benefit, additional cost, failure mode and simpler alternative. If it does not improve a defined metric or acceptance criterion, it is deferred.

# 17. Conclusion

The proposed platform is intentionally more robust than a receipt-upload agent that writes directly to a database, but it avoids building the entire advanced architecture at once. The implementation begins with a thin, deployed vertical slice and adds resilience in the order demanded by the data: validation and review first, correction reuse second, retrieval third, and controlled AI only for remaining uncertainty.

This path balances practical delivery with credible engineering depth. It produces a useful household application while giving the project strong evidence across data engineering, AI engineering, Azure cloud, DevOps, security, testing and cost-aware architecture.

# Appendix A — Initial Repository Structure

expense-intelligence/
  apps/
    api/              FastAPI application and domain services
    web/              Next.js PWA
    worker/           Background receipt processing
  infrastructure/
    bicep/            Reproducible Azure resources
    environments/     Staging and production parameters
  migrations/         Versioned database changes
  tests/
    unit/
    integration/
    e2e/
  .github/workflows/  CI, staging and release pipelines
  docker-compose.yml
  Makefile
  README.md

# Appendix B — Confidence Policy

| Condition | System behavior |
| --- | --- |
| Exact approved mapping | Apply automatically and retain mapping reference |
| Evidence present; confidence ≥0.90 | Suggest automatic approval; log decision and source |
| Confidence 0.70–0.89 | Require user confirmation before persistence |
| Confidence <0.70 | Keep unresolved and offer manual correction |
| No evidence or conflicting evidence | Never auto-approve |
| Receipt fails reconciliation | Block completion regardless of AI confidence |