PROJECT PLAN

# Agent-Assisted Purchase Intelligence Extension

Roadmap after Milestone 1 — receipt normalization, product enrichment, nutrition-oriented purchase insights, and basket-based vendor recommendations

| Current baseline | Working FastAPI application with authentication, households, receipt workflows, OCR, duplicate checks, CRUD, UI, and reporting foundation |
| --- | --- |
| Architecture constraint | Python-only web stack; server-rendered FastAPI UI; no React or Node.js build process |
| Budget constraint | Target operating cost below €5/month for personal-project usage |
| Planning horizon | 10–12 weeks part-time, delivered as independently releasable milestones |

Outcome: Extend the current expense tracker into a traceable system that resolves known products deterministically, researches genuine exceptions with an AI agent, learns from approved mappings, and produces reliable price and purchase-based nutrition insights.

# 1. Delivery principles

Deterministic first: aliases, exact matching, fuzzy matching, calculations, permissions, and database writes remain normal application logic.

Agent only for exceptions: invoke online research when a merchant or item cannot be resolved reliably from approved local data.

Human-in-the-loop: no researched mapping or nutrition record becomes trusted without confidence rules and approval where uncertainty remains.

Source everything: preserve evidence URL, retrieval date, source type, confidence, and raw source payload for externally enriched data.

Household isolation: every workflow must respect the existing household authorization model.

No RAG by default: evaluate pgvector only after a labelled dataset shows an advantage over exact and pg_trgm matching.

Purchases are not consumption: nutrition output describes products purchased, not medical status or actual intake.

# 2. Target architecture

| Layer | Responsibility | Recommended implementation | AI involvement |
| --- | --- | --- | --- |
| Capture | Receipt image and OCR | Existing Azure Document Intelligence flow | None |
| Resolution | Merchant/product normalization | PostgreSQL aliases, exact match, pg_trgm | Agent only after deterministic failure |
| Enrichment | Barcode, package, category, nutrition | Open Food Facts and approved sources | Research and candidate ranking |
| Review | Approve/edit/reject suggestions | FastAPI + Jinja2/HTMX or simple forms | Structured suggestion only |
| Analytics | Price, budget, nutrition totals | SQL/Python services | Explanation of verified results |
| Recommendation | Cheapest useful basket/vendor | Deterministic scoring with freshness and coverage | Research missing current prices |

# 3. Scope and release sequence

| Release | Milestones | User value | Dependency |
| --- | --- | --- | --- |
| Foundation release | 2–4 | Known items normalize and can be reviewed | Milestone 1 |
| Agentic release | 5 | Unknown merchants/items receive sourced candidates | Approved mapping workflow |
| Insight release | 6–7 | Nutrition and price/vendor insights | Reliable normalized products |
| Validation release | 8 | Measured quality, cost, safety, and deployment readiness | Representative usage data |

# 4. Milestone plan

## Milestone 2: Normalized data foundation

Indicative duration: 1.5 weeks
Objective: Create a stable product identity layer without disturbing existing receipt records.

### Implementation work

Add normalized merchant, merchant alias, product, merchant-item mapping, product package, and price-history entities.

Link existing receipt items to a normalized product using nullable foreign keys so migration is backward-compatible.

Store package quantity/unit and derive comparable unit price in application logic.

Add audit fields: source, confidence, approval status, approved by, approved at, created at, and updated at.

Create migrations, model tests, service tests, and household-scoped query helpers.

### Acceptance gate

Existing receipts remain readable and dashboard totals do not change.

A receipt item can be linked to one normalized product without losing raw OCR text.

Unit prices are reproducible for item, kilogram, litre, and standard package cases.

Cross-household reads and writes are rejected by tests.

Agentic-AI contribution: None. This milestone deliberately builds trustworthy data contracts before any agent is introduced.

## Milestone 3: Deterministic merchant and item resolution

Indicative duration: 1.5 weeks
Objective: Resolve repeated merchants and products cheaply and consistently.

### Implementation work

Normalize merchant text using canonical names and deterministic aliases.

Implement exact merchant-specific item mapping.

Enable pg_trgm and add fuzzy candidate search with configurable thresholds.

Return top candidates with match method and score; never silently auto-link ambiguous items.

Record resolution traces for exact, alias, fuzzy, unresolved, and manually selected outcomes.

### Acceptance gate

Known aliases such as merchant legal-name variants resolve consistently.

Previously approved merchant-item mappings are reused without an LLM or internet request.

Ambiguous fuzzy matches remain pending review.

Resolution service meets an agreed local latency target, initially <200 ms excluding OCR.

Agentic-AI contribution: None for normal cases. The unresolved result becomes the explicit trigger for the later research agent.

## Milestone 4: Review and learning workflow

Indicative duration: 1 week
Objective: Let users approve corrections and turn them into reusable mappings.

### Implementation work

Add a household-scoped review queue for unresolved and low-confidence receipt items.

Build server-rendered approve, edit, reject, and leave-unresolved actions.

Show raw OCR text, merchant, candidate, confidence, match method, and evidence when available.

On approval, save a merchant-specific mapping and relink the receipt item transactionally.

Add filters for unresolved, suggested, approved, and rejected records.

### Acceptance gate

A user can complete review without editing database records manually.

A newly approved mapping resolves the next matching item deterministically.

Rejecting a candidate prevents the same unsupported suggestion from being silently reused.

Every approval is attributable to a user and household.

Agentic-AI contribution: Human approval is the control boundary that later allows agent research without granting the model direct database authority.

## Milestone 5: Controlled online research agent

Indicative duration: 2 weeks
Objective: Research only unknown merchants or unresolved products and return evidence-backed candidates.

### Implementation work

Define tools for local mapping search, barcode lookup, Open Food Facts, approved retailer connectors, category taxonomy, and controlled web search.

Implement a small Python state machine: classify case, choose source, search, validate evidence, rank candidates, return structured output.

Use Pydantic schemas for vendor profiles, product candidates, nutrition candidates, confidence, evidence, and failure reasons.

Apply timeouts, per-receipt call limits, caching, retries with bounds, and monthly usage quotas.

Persist an agent run log containing selected tools, source URLs, latency, model, token/usage estimate, result, and user decision.

Require review for new vendor profiles and uncertain product mappings; application services alone perform writes.

### Acceptance gate

Known items never call the research agent.

Every proposed mapping has at least one accessible supporting source or is labelled unresolved.

Malformed, unsupported, or low-confidence outputs cannot update trusted product records.

The system handles unavailable sources and quota exhaustion without breaking receipt capture.

Agent runs are auditable and reproducible enough for portfolio demonstration.

Agentic-AI contribution: This is the core agentic milestone: the agent chooses among tools, follows fallbacks, evaluates evidence, and pauses for human approval.

## Milestone 6: Product and nutrition enrichment

Indicative duration: 1.5 weeks
Objective: Attach sourced, versioned product metadata needed for purchase-oriented nutrition insights.

### Implementation work

Add product identifiers, brand, barcode, category, package metadata, ingredients, allergens, and nutrition snapshots.

Keep nutrition facts versioned with source URL, retrieval time, confidence, and raw payload.

Prefer barcode and Open Food Facts; use official manufacturer/retailer evidence next; research agent handles unresolved products.

Store total sugar separately from any estimated free-sugar field.

Create enrichment status and data-quality flags for missing, conflicting, stale, and user-confirmed records.

Add a product detail/review page using existing server-rendered UI patterns.

### Acceptance gate

Nutrition values always state units and basis, such as per 100 g or per 100 ml.

Conflicting values are visible rather than silently merged.

Missing package quantity blocks aggregate nutrient estimates instead of inventing values.

The UI clearly labels community, official, estimated, and user-confirmed data.

Agentic-AI contribution: The agent may locate and compare nutrition evidence, but it cannot invent values or decide that a user is healthy or unhealthy.

## Milestone 7: Purchase insights and vendor recommendation

Indicative duration: 2 weeks
Objective: Turn normalized purchase history into useful, explainable decisions.

### Implementation work

Implement unit-price history, recent median price, price freshness, coverage, and anomaly detection using SQL/Python.

Build a shopping-list workflow and compare expected basket cost across merchants.

Recommend a single merchant by default; show a multi-store split only when savings exceed a user-defined threshold.

Add purchase-oriented nutrition trends: sugary drinks, confectionery frequency, total labelled sugar purchased, salt, saturated fat, and top contributing products.

Present uncertainty, household scope, period, missing product coverage, and source freshness with every result.

Use the LLM only to explain computed results or research missing/outdated prices; never ask it to calculate totals.

### Acceptance gate

Basket totals can be recomputed from stored price records.

Recommendations show merchant coverage, freshness, missing items, and estimated savings.

Nutrition messages say purchased/estimated, not consumed or diagnosed.

Users can trace every aggregate to receipt items and product metadata.

Agentic-AI contribution: A bounded advisor explains verified trends and may research missing prices; scoring and calculations remain deterministic.

## Milestone 8: Evaluation, optional RAG decision, and deployment hardening

Indicative duration: 1.5 weeks
Objective: Prove that the extension is accurate, economical, safe, and maintainable.

### Implementation work

Build a labelled evaluation set from approved receipt items, including difficult abbreviations and unknown merchants.

Measure exact/fuzzy/agent top-1 accuracy, top-3 recall, automatic-resolution precision, review rate, unsupported-answer rate, latency, and cost per receipt.

Benchmark pg_trgm alone against pg_trgm plus embeddings only after at least 100–200 approved mappings exist.

Add pgvector/RAG only if it improves top-3 recall by roughly 10% without a meaningful precision loss.

Add budget alerts, retention rules, health checks, structured logs, security review, backup/restore test, and failure-mode tests.

Create a demonstration scenario and concise architecture/evaluation documentation.

### Acceptance gate

No agent path can bypass household authorization or review requirements.

Monthly usage remains within the configured budget ceiling under expected personal usage.

Evaluation results justify all automatic-approval thresholds.

RAG is either rejected with evidence or introduced behind a feature flag with measured benefit.

A complete demo traces OCR → resolution → research → approval → reuse → recommendation.

Agentic-AI contribution: Agentic capability is validated through tool-choice traces, evidence quality, human decisions, failure recovery, and measurable usefulness—not by the number of agents.

# 5. Core data additions

| Entity | Purpose | Key fields |
| --- | --- | --- |
| NormalizedMerchant | Canonical merchant identity | household/global scope, name, type, official domain, approval state |
| MerchantAlias | Deterministic merchant matching | merchant_id, raw alias, normalized alias, source |
| Product | Stable normalized product identity | name, brand, barcode, category, status |
| MerchantItemMapping | Raw receipt text → product | merchant_id, raw text, product_id, method, score, approval |
| ProductPackage | Comparable quantity representation | amount, unit, base amount, base unit |
| ProductNutritionSnapshot | Versioned sourced metadata | per-100 values, ingredients, source, retrieved_at, confidence |
| ProductPriceObservation | Auditable price history | receipt_item_id, merchant_id, total price, unit price, promotion flag |
| ResolutionRun | Trace deterministic resolution | input, method, candidates, score, outcome |
| AgentResearchRun | Trace external research | tools, model, evidence, latency, usage, structured result |
| ReviewDecision | Human approval history | candidate, action, user_id, household_id, timestamp |
| ShoppingList/BasketRun | Vendor comparison inputs/results | items, quantities, coverage, freshness, totals |

# 6. Agent contract

Trigger: only after merchant alias, exact mapping, fuzzy matching, and barcode/local-source checks fail or remain below threshold.

Inputs: minimum required receipt-item text, normalized merchant clues, allowed category taxonomy, and prior candidate results.

Tools: local search, barcode/Open Food Facts, approved retailer connector, controlled web search, and taxonomy lookup.

Output: strict structured candidates with normalized identity, attributes, confidence, evidence URLs, source type, and decision status.

Authority: read/search only. The agent cannot approve mappings, alter financial records, or write trusted nutrition facts directly.

Stop conditions: source unavailable, contradictory evidence, quota reached, no supported candidate, or confidence below threshold.

# 7. Testing strategy

| Test level | Focus | Minimum examples |
| --- | --- | --- |
| Unit | Normalization, unit conversion, scoring, confidence rules | Aliases, decimals, kg/L/item, conflicting candidates |
| Database | Migrations, constraints, household isolation | Rollback/forward, unique mappings, cross-household access |
| Integration | OCR item → resolution → review → reuse | Known, fuzzy, unresolved, source failure |
| Agent evaluation | Tool selection and grounded outputs | Unknown merchant, barcode hit, catalogue miss, conflicting evidence |
| UI | Review and recommendation flows | Approve, edit, reject, empty/error states |
| Regression | Existing receipt/dashboard behaviour | Totals, duplicate checks, authentication, household switching |

# 8. Success metrics

| Metric | Meaning |
| --- | --- |
| Deterministic reuse rate | Share of items resolved from approved local mappings without external calls |
| Auto-resolution precision | Correct automatic mappings / all automatic mappings; prioritize precision over coverage |
| Top-3 recall | Correct product appears among the three review candidates |
| Manual-review rate | Share of receipt items still requiring user action |
| Unsupported suggestion rate | Suggestions without adequate source support; target near zero |
| Agent cost and latency | Average and p95 per unresolved item and per receipt |
| Metadata coverage | Products with usable package and nutrition information |
| Basket coverage | Shopping-list items with fresh merchant price evidence |
| User correction reuse | Approved mappings successfully reused on later receipts |

# 9. Risks and controls

| Risk | Control | Owner area |
| --- | --- | --- |
| Retailer pages change or block automation | Prefer APIs and approved connectors; cache evidence; fail to review queue | Agent integration |
| Wrong product silently linked | High precision threshold, top candidates, approval for uncertainty | Resolution |
| Nutrition data incomplete or conflicting | Versioned sources, quality flags, no invented values | Enrichment |
| Purchase interpreted as consumption | Wording rules and visible methodological limitation | Analytics/UI |
| Agent cost grows unexpectedly | Exception-only trigger, quotas, caching, usage logs, no paid fallback | Operations |
| Household data leakage | Scope every query, authorization tests, minimize agent input | Security |
| RAG added without benefit | Benchmark gate and feature flag | Evaluation |
| Scope expansion delays delivery | Release each milestone independently; defer optional features | Project management |

# 10. Definition of done for the extended project

Existing Milestone 1 workflows remain stable and covered by regression tests.

Known items resolve locally; unresolved items follow a controlled research and review path.

Approved corrections are reused and measurably reduce future manual work.

Nutrition and price metadata are sourced, versioned, and traceable.

Vendor recommendations show price coverage, freshness, assumptions, and estimated savings.

Purchase-oriented nutrition insights avoid medical claims and trace back to receipt items.

Agent actions are bounded, auditable, failure-tolerant, and within budget.

RAG is included only if the evaluation gate proves value.

Architecture, setup, evaluation dataset, metrics, limitations, and demonstration flow are documented.

# 11. Immediate next sprint

Recommended starting point: Implement Milestone 2 only. Do not start the research agent until the normalized product model, merchant-specific mappings, package units, price observations, migrations, and household-scoped tests are stable.

Map the current SQLAlchemy models, Alembic migrations, services, routes, and templates that touch receipt items.

Write a migration proposal for normalized merchants, products, mappings, packages, and price observations.

Define backward-compatible relationships from current Merchant and ReceiptItem records.

Add unit conversion and unit-price tests before exposing new UI.

Seed five representative merchants and 20–30 real receipt-item variants for development tests.

Confirm the Milestone 2 schema in a short architecture decision record before implementation.

Plan assumption: the repository matches the user-confirmed Milestone 1 baseline. Exact file-level tasks should be refined after inspecting the latest source repository.